## Sheet1
PROJECT SCHEDULE
Project Title: | Kangaroo
Members: | Damian, Natelie
Duration: | 12 Jan ~ 4 March
TASKS | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8
Project Planning | Damian, Natelie | Damian, Natelie
Storyboard Layout | Damian, Natelie | Damian, Natelie
Login Page (Design) | Damian, Natelie | Damian, Natelie
Login Page (Coding) |  | Damian
Forgot Password Page (Design) |  | Damian
Forgot Password Page (Coding) |  | Damian | Damian, Natelie
Registration Page (Design) |  | Damian, Natelie | Damian, Natelie
Registration Page (Coding) |  |  | Damian, Natelie
Home Page (Design) |  |  | Damian, Natelie | Damian, Natelie
Home Page (Coding) |  |  | Damian | Damian | Damian | Damian
Products Page (Design) |  |  |  | Damian, Natelie | Damian, Natelie | Damian, Natelie
Products Page (Coding) |  |  |  | Damian | Damian | Damian | Damian
Cart Page (Design) |  |  |  |  | Damian, Natelie | Damian, Natelie | Damian, Natelie
Cart Page (Coding) |  |  |  |  | Damian | Damian | Damian
Checkout Page (Design) | [5 empty] | Damian, Natelie | Damian, Natelie
Checkout Page (Coding) | [5 empty] | Damian | Damian, Natelie
Delivery Page (Design) | [6 empty] | Damian, Natelie
Delivery Page (Coding) | [6 empty] | Damian, Natelie | Damian, Natelie
Account Page (Design) | [6 empty] | Damian, Natelie | Damian, Natelie
Account Page (Coding) | [7 empty] | Damian
Top-up Page (Design) | [7 empty] | Damian, Natelie
Top-up Page (Coding) | [7 empty] | Damian, Natelie
Wishlist Page (Design) | [7 empty] | Damian, Natelie
Wishlist Page (Coding) | [7 empty] | Damian
Testing | [7 empty] | Damian, Natelie
Documentation | [7 empty] | Damian, Natelie
Presentation | [7 empty] | Damian, Natelie